## Sheet1
Fluke Calibration
New Product Release Forecast
Note this is confidential information and should be strictly limited to those with a legitimate need to know.
Forecast PAA date as of:
Project Name | Family | Description | BC | PDP | CRR | PRR | MRR | PAA |  | 2011-04-12 | 2011-06-13 | 2012-07-18
M/C 7.3 SP1 | SWCAL | [8 empty] | Launched
MMC 2.1 | SWCAL | [8 empty] | Launched
Beamex | TCAL | Beamex-branded Metrology Wells and Field Metrology Wells | Done | Done | Done | Done | 2011-05-15 | n/a |  | 2011-05-15
Compass 4.0 | SWCAL | Pessure Calibration software | N/A | Done | N/A | N/A | 2011-08-11 | 2011-09-11 |  | 2011-06-15 | 2011-07-11 | 2011-09-11
PG9602 | PCAL | NMI Piston Guage, Higher Pressure Supplement to PG9607 | Done | Done | 2011-08-30 | 2011-08-30 | 2011-08-30 | 2011-09-30 |  | 2011-06-15 | 2011-08-30 | 2011-09-30
MET/CAL 8.0 | SWCAL | New procedure editor, new library FSC, new FSCs | Done | Done | 2011-08-11 | 2011-09-11 | 2011-10-15 | 2011-11-15 |  | 2011-10-15 | 2011-10-15 | 2011-11-15
Cadmus | ECAL | 120A Transconductance Amplifier - used with | Done | Done | Done | 2011-12-12 | 2012-02-13 | 2012-03-13 |  | 2011-07-29 | 2011-11-11 | 2012-03-13
MET/TRACK 2012 | SWCAL | Brower based asset management software | 2011-08-12 | 2011-11-11 | 2011-11-11 | 2012-01-15 | 2012-03-15 | 2012-04-15 |  | 2012-03-15 | 2012-03-12 | 2012-04-15
M/C 9.0 | SWCAL | MET/CAL runtime software that works with M/T 2012 | 2011-08-12 | 2011-11-11 | 2011-11-11 | 2012-01-15 | 2012-03-15 | 2012-04-15 |  | 2012-03-15 | 2012-03-12 | 2012-04-15
PMU Calibrator | ECAL | PMU Calibrator - based on 61XX Platform | Done | 2011-07-11 | Done | 2011-12-11 | 2012-04-15 | 2012-05-15 |  |  | 2012-01-01 | 2012-05-15
Zhurong (9112C) | TCAL | MPP Thermocouple Calibration Furnace, IC planned for 4/25 | 2011-08-11 | 2011-11-15 | 2012-04-01 | 2012-03-01 | 2012-06-01 | 2012-07-01 |  | 2012-05-15 | 2012-05-12 | 2012-07-01
ChenXiang | PCAL | Round gauges | TBD | TBD | TBD | TBD | 2012-06-30 | 2012-07-28 |  |  | n/a | 2012-07-28
Ultra (9190) | TCAL | Ultra-Cool Dry-Well Calibrator (–95 °C) | Done | 2011-08-11 | 2012-08-12 | 2012-10-12 | 2013-02-01 | 2013-03-01 |  |  | n/a | 2013-03-01
MTV A | TCAL | Precision Temperature Calibration System | Done | Done | 2012-11-01 | 2012-12-01 | 2013-03-01 | 2013-04-01 |  | 2011-11-15 | 2012-05-12 | 2013-04-01
MTV B | DATA | Multi-parameter temperature scanner/recorder | Done | 2011-07-15 | 2011-09-09 | 2012-12-12 | 2013-03-15 | 2013-04-15 |  | 2011-11-15 | 2012-05-12 | 2013-04-15
Newport | PCAL | Navy High Gas Pressure Portable Calibration System | Done | 2011-10-30 | 2012-05-15 | 2013-03-15 | 2013-06-15 | 2013-07-15 |  | 2012-09-15 | 2013-06-30 | 2013-07-15
Note: PAA date should be 4 weeks after MRR date.
This forecast should include all projects expected to launch before end of 2012.
Note on F15: davep: we will be re-doing this CRR with Rick Pirret at the helm - but of no real consequence to this sheet
Note on A17: This will be called MET/CAL 8X, and will coincide with MET/TRACK 2012 release
Note on A21: This row was added, and we will really know exact schedule at PDP.
Note on E24: msearle: Dates are dependent on RFP from US Navy We did have this as before proposal - changed to after award (have more complete PDP)
Note on F24: msearle: Dates are dependent on RFP from US Navy
Note on G24: msearle: Dates are dependent on RFP from US Navy
Note on H24: msearle: Dates are dependent on RFP from US Navy
Note on I24: msearle: Dates are dependent on RFP from US Navy
Note on M24: msearle: Dates are dependent on RFP from US Navy
Note on N24: msearle: Dates are dependent on RFP from US Navy